## Trang tính1
Document Reviewer Information
Reviewer Name | Review Attendance (R/S) | Comments
Document Approver Information
Approver Name | Approver Function | Comments
Document Revision History
Date | Revision | Status | Change Summary | Revised by

## Trang tính2
Defect report (System test)
Defect ID | Defect title | Assigned to | State | Priority (1,2,3,4) | Severity (1,2,3,4) | Occurences | Created by | Date created | Re-produce steps | Detail | System info | Related Testcase ID
LOGIN - SIGN UP
ID01 | Log in to your account | Thuận | Close | 3 | 3 | Điền đủ và đúng thông tin cần thiết nhưng không đăng nhập được | Tú Anh | 2024-11-25 | 1. Họ tên 2. Mật khẩu 3. Đăng nhập | sprint 2 |  | R-TC1
ID02 | Log in to your account | Thuận | Close | 3 | 3 | Nhập sai mật khẩu nhưng không thông báo cho người dùng mà thông báo thành công | Phong | 2024-11-28 | 1. Nhập tên tài khoản 2. Nhập mật khẩu sai 3. Bấm nút đăng nhập | sprint 2 |  | QLCH_TK05
ID03 | Register an account | Thuận | Close | 3 | 3 | Nhập email, tên tài khoản đã tồn tại mà vẫn thông báo thành công | Phong | 2024-11-28 | 1. Nhập tên tài khoản đã trùng 2. Nhập mật khẩu 3. Nhập Email đã trùng 4. Nhập số điện thoại 5. Ấn đăng ký | sprint 2 |  | QLCH_TK06
ID04 | Save login information | Thuận | Close | 3 | 3 | Đăng ký nhưng kiểm tra database chưa có thông tin vừa nhập | Tôn | 2024-11-25 | 1. Nhập tên tài khoản mới 2. Nhập mật khẩu mới 3. Nhập Email chưa có 5. Ấn đăng ký | sprint 2 |  | QLCH_TK09
ID05 | Registration page link | Thuận | Close | 3 | 3 | Ấn chuyển trang ở câu hỏi chưa có tài khoản thì không chuyển được | Tôn | 2024-11-25 | 1. Ấn chuyển trang khi chưa có tài khoản 2. Trang đăng ký được giữ nguyên | sprint 2 |  | QLCH_TK10
MENU
ID06 | Lỗi liên kết sai trong mục "Sản phẩm - Labubu" | Phong | Close | 3 | 1 | Khi nhấn vào mục "Labubu", người dùng bị điều hướng đến trang sản phẩm "Capypara". | Tú Anh | 2024-11-11 | 1. Mở trang web 2. Di chuột vào mục sản phẩm. 3. Kích vào mục Labubu trong danh sách xổ xuống 4. Trang chuyển sang trang sản phầm Capypara | sprint 2 |  | R-TC15
ID07 | Không giữ trạng thái active | Phong | Close | 2 | 2 | Lỗi logic trong CSS hoặc không cập nhật trạng thái active khi chuyển trang. | Phong | 11/28/2024 | 1. Di chuột qua hoặc nhấp vào mục menu có dropdown. 2. Khi dropdown mở ra, di chuột ra ngoài hoặc nhấn vào mục khác. 3. Quan sát xem dropdown có tự động đóng trước khi hoàn tất thao tác không. | sprint 2 |  | ST-F-MH04
SLIDE-SHOW
ID08 | Button điều hướng không hoạt động (Phần banner) | Phong | Close | 3 | 3 | Nút điều hướng (trái - phải) không hoạt động khi kích vào | Tú Anh | 2024-11-16 | 1. Mở trang web 2. Cuộn chuột xuống phần banner 3. Nhấn vào nút chuyển ảnh bên trái hoặc phải. 4. Ảnh không thay đổi. | sprint 2 |  | R-TC22
ID09 | Ảnh không hiển thị | Phong | Close | 4 | 2 | Vài ảnh hiển thị vài ảnh không hiển thị | Hân | 2024-11-17 | 1. Mở web 2. Kéo xuống slide - show | sprint 2 |  | R-TC26
ID10 | Slide hoạt động trên thiết bị di động không như ý muốn | Phong | Close | 2 | 3 | Responsive của slide bị lỗi tỉ lệ | Phong | 11/28/2024 | 1. Truy cập vào trang web có slide-show. 2. Mở Developer Tools (F12) > Tab Console. 3. Đổi tỉ lệ màn hình sang thiết bị di động. | sprint 2
COMBO - SHOW
ID11 | Combo-show không tương thích trên màn hình nhỏ (Phần Combo Siêu Hot) | Phong | Close | 2 | 3 | Trên thiết bị có màn hình nhỏ hơn,combo-show hiển thị không đúng kích thước, ảnh bị tràn ra ngoài | Tú Anh | 2024-11-18 | 1. Mở trang web 2. Thu nhỏ kích thước trình duyệt về di dộng 3. Cuộn chuột xuống phần Combo Siêu Hot 4. Quan sát thấy slide-show bị cắt và tràn ra ngoài khung nhìn. | sprint 2 |  | R-TC29
ID12 | Không thể tự tay chuyển hình ảnh được | Phong | Close | 1 | 1 | Khi bấm giữ chuyển kéo ảnh không hoạt động | Phong | 11/28/2024 | 1. Dùng chuột bấm giữ kéo sang trái, phải 2. Quan sát xem ảnh có di chuyển không | sprint 2 |  | ST-F-DH06
PRODUCT MANAGEMENT
ID13 | Sửa thông tin sản phẩm không thành công | Phong | Close | 3 | 3 | Khi admin chỉnh sửa thông tin của sản phẩm, các thay đổi không được lưu lại. | Tú Anh | 2024-11-19 | 1. Mở trang web 2. Đăng nhập vào trang admin. 3. Vào các trang sản phẩm 4. Chọn một sản phẩm và cập nhật thông tin 5. Thay đổi thông tin : sửa giá tiền 6. Nhấn "Lưu". 7. Tải lại trang, thông tin sản phẩm vẫn là giá cũ. | sprint 3 |  | R-TC45
ID14 | Sửa thông tin không được | Phong | Close | 3 | 3 | Sửa thành hết sản phẩm bấm lưu không được | Hân | 2024-11-20 | 1. Vào sản phẩm Capybara 2. Sửa 3. Bấm lưu | sprint 3 |  | R-TC45
ID15 | Lỗi không sửa được ảnh | Phong | Close | 3 | 2 | Đổi ảnh nhưng lưu vẫn là ảnh cũ | Hân | 2024-11-21 | 1. Vào sản phẩm Capybara 2. Sửa 3. Bấm lưu | sprint 3 |  | R-TC45
ADD TO CART
ID16 | Giao diện sai màu | Phong | Close | 3 | 1 | Nền giỏ hàng sai màu | Hân | 11/28/2023 | 1. Vào web 2. Vào giỏ hàng | sprint 3 |  | R-TC37
ID17 | Chậm khi thêm nhiều sản phẩm vào giỏ hàng | Phong | Close | 3 | 3 | Trang phải xử lý nhiều sản phẩm mất nhiều thời gian. | Phong | 11/28/2024 | 1. Thêm nhiều sản phẩm vào giỏ hàng trong một khoảng thời gian ngắn. 2. Quan sát độ trễ trong giao diện khi giỏ hàng cập nhật. | sprint 3 |  | R-TC37
ID18 | Sai trang điều hướng | Phong | Close | 3 | 3 | Khi nhấn vào add to cart thì điều hướng sang trang cẩm nang | Thuận | 11/28/2024 | 1. Vào web 2. Nhấn vào một sản phẩm 3. Nhấn vào sản phẩm 4. Đã điền đầy đủ thông tin 5. Click vào add to cart 6. Điều hướng sang trang cẩm nag | sprint 3 |  | R-TC37
ID19 | Sản phẩm đã hết hàng nhưng vẫn cho phép thêm | Phong | Close | 1 | 3 | Khi sản phẩm đã được thông báo đến người dùng là hết hàng nhưng sản phẩm vẫn được thêm vào giỏ hàng của người mua | Thuận | 11/28/2024 | 1. Vào web 2. Nhấn vào 1 trang sản phẩm 3. Nhấn vào sản phẩm cần mua 4. Điền đầy đủ thông tin 5. Sản phẩm được thông báo đã hết hàng 6. Nhưng khi nhấn vào add to cart thì sản phẩm vẫn được thêm giỏ hàng | sprint 3 |  | R-TC37

## Trang tính3
Defect report (Unit test)
Defect ID | Defect title | Assigned to | State | Priority (1,2,3,4) | Severity (1,2,3,4) | Occurences | Created by | Date created | Re-produce steps | Detail | System info | Related Testcase ID
ConnectData.cs
UT-DF-CD01 | GetTopDataCell(string nameTable, string nameSelectColumn, string orderByColumn) | Tuan Ly | Close | 1 | 2 | This Function return wrong value | Phuong Le | 2011-04-08 | Execute GetTopDataCell(string nameTable, string nameSelectColumn, string orderByColumn) with parameters are: NHOMHANG, MANHAN, MANHAN | In table NHOMHANG don't have column MANHAN, but this function return value 55 |  | UT-CD03
KhuyenMaiCtrl.cs
UT-DF-KMC01 | KiemTraTruocKhiLuu(DataTable dtbKhuyenMai, String cellString) | Hung Tran | Close | 1 | 1 | This function can't test TENKM when it is null | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbKhuyenMai, String cellString) with parameters are: (2,"",1, 19/8/2011, 4/8/2011), "TenKM" | It miss check TenKM be null |  | UT-KMC01
UT-DF-KMC02 | KiemTraTruocKhiLuu(DataTable dtbKhuyenMai, String cellString) | Hung Tran | Close | 1 | 1 | This function can't test TENKM when it is more 50 characters | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbKhuyenMai, String cellString) with parameters are: (2,“Chương trình khuyến mãi mừng ngày Thầy thuốc Việt Nam 27-2”1, 19/8/2011, 4/8/2011), "TenKM" | It miss check TenKM be more 50 characters |  | UT-KMC01
MatHangKhuyenMaiCtrl.cs
UT-DF-MHKMC01 | KiemTraTruocKhiLuu(DataTable dtbMatHangKhuyenMai, String cellString) | Hung Tran | Close | 1 | 1 | This function can't check the product is be sale off in other program | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbKhuyenMai, String cellString) with parameters are: (2 ,54,1 ,5/08/2011 12:00:00 SA ,10/08/2011 12:00:00 SA, 4000), "MaMH" (2,53 ,1, 5/08/2011 12:00:00 SA ,10/08/2011 12:00:00 SA, 4000),"MaMH" | The Product with code 53,54 is promoting in first program, but in second it add a new program with beginning when the first program hasn't finished. |  | UT-MHKMC01
NhaCungCapCtrl.cs
UT-DF-NCCC01 | KiemTraTruocKhiLuu(DataTable dtbNhaCungCap, String cellString) | Anh Lam | Close | 1 | 2 | This function can't test TenNhaCungCap when it is more 100 characters | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbNhaCungcap, String cellString) with parameters are: 1,CÔNG TY TRÁCH NHIỆM MỘT THÀNH VIÊN THỰC PHẨM DINH DƯỠNG VÀ NƯỚC GIẢI KHÁT MIỀN NAM – PEPPCOO1,“0831854245”,“1795178572”,TPHCM,“081672172”,1,TenNhaCungCap | It miss check TenNhaCungCap be more 100 characters |  | UT-NCCC01
UT-DF-NCCC02 | KiemTraTruocKhiLuu(DataTable dtbNhaCungCap, String cellString) | Anh Lam | Close | 1 | 2 | This function can't test SoDT when it is more 20 characters and include numbers | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbNhaCungcap, String cellString) with parameters are: 1,GRAFIGHT,083185424508318542451,1795178572,TPHCM,081672172,1,SoDT | It miss check SoDT be more 20 characters |  | UT-NCCC01
UT-DF-NCCC03 | KiemTraTruocKhiLuu(DataTable dtbNhaCungCap, String cellString) | Anh Lam | Close | 1 | 2 | This function can't test SoTaiKhoan when it is more 20 characters | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbNhaCungcap, String cellString) with parameters are: 1,GRAFIGHT,“0831854245”,“1795178572D1795178572”,TPHCM,“081672172”,1,SoTaiKhoan | It miss check SoTaiKhoan be more 20 characters |  | UT-NCCC01
UT-DF-NCCC04 | KiemTraTruocKhiLuu(DataTable dtbNhaCungCap, String cellString) | Anh Lam | Close | 1 | 2 | This function can't test SoTaiKhoan with special characters | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbNhaCungcap, String cellString) with parameters are: 1,GRAFIGHT,“0831854245”,“1795178572D1795178$”,TPHCM,“081672172”,1,SoTaiKhoan | SoTaiKhoan can't have special characters |  | UT-NCCC01
UT-DF-NCCC05 | KiemTraTruocKhiLuu(DataTable dtbNhaCungCap, String cellString) | Anh Lam | Close | 1 | 2 | This function can't test DChi when it is more 100 characters | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbNhaCungcap, String cellString) with parameters are: 1,GRAFIGHT,“0831854245”,“1795178572”,57-59-61-63/159/12/9923 NGUY?N TH? MINH KHAI - PHƯ?NG TR?N HƯNG Đ?O - THÀNH PH? V?NG TÀU - BÀ R?A V?NG TÀU,“081672172”,1,Dchi | Dchi cannot null anh less 100 characters
UT-DF-NCCC06 | KiemTraTruocKhiLuu(DataTable dtbNhaCungCap, String cellString) | Anh Lam | Close | 1 | 2 | This function can't test SoFax when it is more 20 characters and include numbers | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbNhaCungcap, String cellString) with parameters are: 1,GRAFIGHT,“0831854245”,“1795178572”,TPHCM,“083185424508318542451”,1,SoFax,false | It miss check SoFax be more 20 characters
MatHangCtrl.cs
UT-DF-MHC01 | KiemTraTruocKhiLuu(DataTable dtbMatHang, String cellString) | Thanh Tran, Tram Tran | Close | 1 | 1 | It can't check same barcode | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbMatHang, String cellString) with parameters are: 2,“8012441555100”, GILLETTE FUSION PROGLIDE , 100 , P&G , False , NULL , CÁI ,8000, 17,MaVach | It is same product barcode in store |  | UT-MHC01
UT-DF-MHC02 | KiemTraTruocKhiLuu(DataTable dtbMatHang, String cellString) | Thanh Tran, Tram Tran | Close | 1 | 1 | TenMH is more 50 characters | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbMatHang, String cellString) with parameters are: 2,“8012441555101”, D?u g?i đ?u ADVANCE TECHNIQUES Body Building Shampoo , 100 , P&G , False , NULL , CÁI ,8000, 17, TENMH | It miss check TenMH be more 50 characters |  | UT-MHC01
UT-DF-MHC03 | KiemTraTruocKhiLuu(DataTable dtbMatHang, String cellString) | Thanh Tran, Tram Tran | Close | 1 | 1 | NSX is more 100 characters | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbMatHang, String cellString) with parameters are: 2,“8012441555101”, SODA , 100 , CÔNG TY TRÁCH NHI?M M?T THÀNH VIÊN TH?C PH?M DINH DƯ?NG VÀ NƯ?C GI?I KHÁT MI?N NAM – PEPPCOO1 , False , NULL , CÁI ,8000, 17, NSX,false | It miss check NSX be more 100 characters |  | UT-MHC01
UT-DF-MHC04 | KiemTraTruocKhiLuu(DataTable dtbMatHang, String cellString) | Thanh Tran, Tram Tran | Close | 1 | 1 | DVTinh is more 10 character | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbMatHang, String cellString) with parameters are: 2,“8012441555101” , GILLETTE FUSION PROGLIDE , 100 , P&G , False , NULL , THÙNG NƯ?C1 ,8000, 17,DVTINH | It miss check DVTinh be more 10 characters |  | UT-MHC01
UT-DF-MHC05 | KiemTraTruocKhiLuu(DataTable dtbMatHang, String cellString) | Thanh Tran, Tram Tran | Close | 1 | 1 | GIABAN is a negative number | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbMatHang, String cellString) with parameters are: 2,“8012441555101”, GILLETTE FUSION PROGLIDE , 100 , P&G , False , NULL , CÁI ,-8000, 17,GIABAN | GIABAN must be position number, but when GIABAN < 0 this test case pass |  | UT-MHC01
MatHangData.cs
UT-DF-MHD01 | SaveToDB(string MaMH, string TenMH, string MaVach,string DonGiaMua, string DonGiaBan, string DonViTinh,string SoLuongTon, string NhaSanXuat,string MaNH) | Thanh Tran, Tram Tran | Close | 1 | 1 | It is inserted to database | Phuong Le | 2011-04-08 | Execute SaveToDB(string MaMH, string TenMH, string MaVach,string DonGiaMua, string DonGiaBan, string DonViTinh,string SoLuongTon, string NhaSanXuat,string MaNH) with parameters are: 2,“8012441555101”, GILLETTE FUSION PROGLIDE , 100 , P&G , False , NULL , CÁI ,-8000,0, 17,0 | GIABAN must be position number, but it be inserted to database |  | UT-MHD01
UT-DF-MHD02 | SaveToDB(string MaMH, string TenMH, string MaVach,string DonGiaMua, string DonGiaBan, string DonViTinh,string SoLuongTon, string NhaSanXuat,string MaNH) | Thanh Tran, Tram Tran | Close | 1 | 1 | It is inserted to database | Phuong Le | 2011-04-08 | Execute SaveToDB(string MaMH, string TenMH, string MaVach,string DonGiaMua, string DonGiaBan, string DonViTinh,string SoLuongTon, string NhaSanXuat,string MaNH) with parameters are: 2,“8012441555101”, D?u g?i đ?u ADVANCE TECHNIQUES Body Building Shampoo , 100 , P&G , False , NULL , CÁI ,8000,0, 17 | It miss check TenMH be more 50 characters |  | UT-MHD01

## defect_report_Tiếng Anh
Defect report (System test)
Defect ID | Defect title | Assigned to | State | Priority (1,2,3,4) | Severity (1,2,3,4) | Occurences | Created by | Date created | Re-produce steps | Detail | System info | Related Testcase ID
LOGIN - SIGN UP
ID01 | Log in to your account | Thuận | Close | 3 | 3 | Fill in the required information completely and correctly but can't log in | Tú Anh | 2024-11-25 | 1. Full name 2. Password 3. Log in | sprint 2 |  | R-TC1
ID02 | Log in to your account | Thuận | Close | 3 | 3 | Enter the wrong password but do not notify the user but notify the user successfully | Phong | 2024-11-28 | 1. Enter account name 2. Enter the wrong password 3. Click the login button | sprint 2 |  | QLCH_TK05
ID03 | Register an account | Thuận | Close | 3 | 3 | Enter email and account name that already exists and still receive a success message | Phong | 2024-11-28 | 1. Enter the duplicate account name 2. Enter password 3. Enter the duplicate Email 4. Enter the phone number 5. Click register | sprint 2 |  | QLCH_TK06
ID04 | Save login information | Thuận | Close | 3 | 3 | Registered but checked the database and did not have the information just entered | Tôn | 2024-11-25 | 1. Enter a new account name 2. Enter a new password 3. Enter an email that doesn't exist yet 5. Click register | sprint 2 |  | QLCH_TK09
ID05 | Registration page link | Thuận | Close | 3 | 3 | If you press page change in the question, if you don't have an account, you won't be able to move | Tôn | 2024-11-25 | 1. Click to change page if you don't have an account 2. The registration page remains the same | sprint 2 |  | QLCH_TK10
MENU
ID06 | Wrong link error in "Products - Labubu" section | Phong | Close | 3 | 1 | When clicking on the "Labubu" item, the user is redirected to the "Capypara" product page. | Tú Anh | 2024-11-11 | 1. Open the website 2. Hover your mouse over the product section. 3. Click on Labubu in the drop-down list 4. The page switches to the Capypara product page | sprint 2 |  | R-TC15
ID07 | Do not keep active status | Phong | Close | 2 | 2 | Logical error in CSS or not updating active state when switching pages. | Phong | 11/28/2024 | 1. Hover over or click the dropdown menu item. 2. When the dropdown opens, move the mouse out or click on another item. 3. Observe whether the dropdown automatically closes before completing the operation. | sprint 2 |  | ST-F-MH04
SLIDE-SHOW
ID08 | Navigation button not working (Banner part) | Phong | Close | 3 | 3 | Navigation buttons (left - right) do not work when clicked | Tú Anh | 2024-11-16 | 1. Open the website 2. Scroll down to the banner section 3. Click the photo transfer button on the left or right. 4. Photos do not change. | sprint 2 |  | R-TC22
ID09 | Photos are not displayed | Phong | Close | 4 | 2 | Some photos show up, some don't show up | Hân | 2024-11-17 | 1. Open the website 2. Scroll down the slide - show | sprint 2 |  | R-TC26
ID10 | Slide doesn't work as expected on mobile devices | Phong | Close | 2 | 3 | Responsiveness of the slide has a proportional error | Phong | 11/28/2024 | 1. Visit a website with a slide-show. 2. Open Developer Tools (F12) > Console Tab. 3. Change the screen ratio to mobile devices. | sprint 2
COMBO - SHOW
ID11 | Combo-show is not compatible on small screens (Super Hot Combo Section) | Phong | Close | 2 | 3 | On devices with smaller screens, the combo-show is displayed at the wrong size and the image overflows | Tú Anh | 2024-11-18 | 1. Open the website 2. Reduce browser size to mobile 3. Scroll down to the "Super Hot Combo" section 4. Observe that the slide-show is cut off and overflows outside the viewport. | sprint 2 |  | R-TC29
ID12 | Images cannot be transferred manually | Phong | Close | 1 | 1 | When pressing and holding, moving and dragging the image does not work | Phong | 11/28/2024 | 1. Use the mouse to click and drag left and right 2. Observe whether the image moves | sprint 2 |  | ST-F-DH06
PRODUCT MANAGEMENT
ID13 | Editing product information failed | Phong | Close | 3 | 3 | When admin edits product information, changes are not saved. | Tú Anh | 2024-11-19 | 1. Open the website 2. Log in to the admin page. 3. Go to product pages 4. Select a product and update the information 5. Change information: edit price 6. Click "Save". 7. Reload the page, the product information is still the old price. | sprint 3 |  | R-TC45
ID14 | Cannot edit information | Phong | Close | 3 | 3 | Editing all products cannot be saved | Hân | 2024-11-20 | 1. Go to Capybara product 2. Edit 3. Click save | sprint 3 |  | R-TC45
ID15 | Error unable to edit image | Phong | Close | 3 | 2 | Change the photo but save it as the old photo | Hân | 2024-11-21 | 1. Go to Capybara product 2. Edit 3. Click save | sprint 3 |  | R-TC45
ADD TO CART
ID16 | Wrong color interface | Phong | Close | 3 | 1 | Cart background color is wrong | Hân | 11/28/2023 | 1. Go to the website 2. Go to cart | sprint 3 |  | R-TC37
ID17 | Slow when adding many products to cart | Phong | Close | 3 | 3 | The page has to process many products which takes a lot of time. | Phong | 11/28/2024 | 1. Add more products to the cart in a short period of time. 2. Observe the delay in the interface as the shopping cart updates. | sprint 3 |  | R-TC37
ID18 | Wrong navigation page | Phong | Close | 3 | 3 | When you click add to cart, you will navigate to the handbook page | Thuận | 11/28/2024 | 1. Go to the website 2. Tap a product 3. Click on the product 4. Completed information 5. Click add to cart 6. Navigate to the manual page | sprint 3 |  | R-TC37
ID19 | The product is out of stock but refills are still available | Phong | Close | 1 | 3 | When the product has been notified to the user that it is out of stock but the product is still added to the buyer's cart | Thuận | 11/28/2024 | 1. Go to the website 2. Click on a product page 3. Click on the product you want to buy 4. Fill in all information 5. The product is reported to be out of stock 6. But when clicking add to cart, the product is still added to the cart | sprint 3 |  | R-TC37